## Plan
Week By Week Development Plan for Pose Estimation:
Data and Inputs
Calibrated data for Wankhede already shared
Stabilised frame level data from Goa (3 Cams) - Mar 15, 2025 - 13 clips
Triangulation matrices
Specific problematic data with occlusions and jittery pose. ( Still to be manually found)
[5 empty] | Week Summary |  | Bottlenecks
Deliverables: | Week 1: Foundation |  |  |  | 2D | 3D
Goals: Set up baseline understanding and distribute objectives. | All Members: |  |  | Team C (Vatsal, Simone, Souymadeep, Manu)
Internal tech talk per member on findings. | Review RTMPose2D model architecture and inference pipeline. |  |  | Identify a test data set which is not used in training, but is used for evaluation at the end of each week | Add the week1 summary here | Add the week1 summary here
Understand current confidence score generation.
Set up personal dev environments (model loading, sample footage).
Week 2: 2D Confidence Handling
Basic filtering module for 2D points. | Team A (2D focus): | Team B (3D focus): |  | Team C (Vatsal, Simone, Souymadeep, Manu)
Visualization of before/after filtering on multiple clips. | Analyze confidence scores per keypoint over video frames. | Study how confidence scores from 2D affect 3D triangulation accuracy.
| Identify thresholds for dropping noisy/low confidence points - Is < 0.6 then probably not good to use | Simulate triangulation with and without low-confidence keypoints. - Use Blender to review |  | Collecting training data for bats using the optitrack system.
Begin documenting initial reprojection error trends.
| Week end: Output 2D points removing noisy/low confidence values - Provided heatmaps | Week end: Report on identified low confidence points and the impact on final 3D movement |  |  | Add the week2 summary here | Add the week2 summary here
Week 3: Occlusion in 2D
Occlusion handling prototype (linear interpolation). | Team A (2D focus): | Team B (3D focus):
Metrics dashboard to measure impact on keypoints. | Identify frames with occluded (<0.6 confidence) joints (manual + algorithmic approach). | Define how occluded 2D points affect triangulation — test and compare frame-by-frame stability. |  | Provide 10 x runout clips from 15th March to interns, including the 2D, 3D and BVH data
| Implement temporal interpolation using last-known valid positions (linear + Kalman). Including arm and leg swaps 1. Kalman filter 2. Unscented Kalman filter 3. Bayesian netwrok [https://filterpy.readthedocs.io/en/latest/kalman/UnscentedKalmanFilter.html] | Define error metrics for 3D pose point accuracy e.g. displacement of joints - 3d point? rotation error - BVH? Reprojection error? |  | Explain to interns how to use blender
| Any new pose algorithms that have come out - share the benchmarking (jitter and occlusion handling) | Algorithms where bones can be added |  | Reproject ground truth data from optitrack system on to 2D images collected from the cameras
| Week end: Report on temporal enhancements for 2D occluded points (before and after results on test data set) | Week end: Report on temporal enhancements for 3D points (before and after results on test data set) |  | Experimentation with Optitrack data, focusing on the bat. | Add the week3 summary here | Add the week3 summary here
Week 4: Temporal Smoothing |  |  |  | Establish livelink pipeline - 1 month
Before/after comparison of skeleton smoothness (2D & 3D). | Team A (2D focus): | Team B (3D focus):
Qualitative + quantitative evaluation doc. | Implement basic temporal smoothing (Moving Average). | Using temporal 2D points (from Team A output week 3). Log scenarios where 3D temporal data improves or degrades triangulation.
|  | Add in root node 3D coordinate into BVH | -> | Analysis drifting of root node, causing "skating" effect
| Prototype occlusion flagging system based on joint visibility + confidence, and automatic rejection mechanism based on median/local average confidence. | Review and evaluate methods for temporal smoothing on 3D points. Should and could low confidence points be weighted for increased adjusted? Savitzky–Golay
| Test against jitter and occlusion-filled sequences. | Explore kinetic model approach for refining of points and contraints on "impossible" movement E.g. elbow or knees bending backwards
| Week end: Review on temporal exploration on 2D point accuracy | Week end: Review of impact of 2D temporal data and using kinetic contraints |  |  | Add the week4 summary here | Add the week4 summary here
Week 5: Mid-Point Integration & Feedback
Integrated prototype. | All Members:
Debug report with priority issues + success cases. | Integrate 2D and 3D modules into unified prototype pipeline. | Apply smoothed 2D data to existing triangulation.
| Run full test passes on 2-3 deliveries. | Compare 3D skeletons pre- and post-smoothing.
Team review session: what’s working, what’s not?
Week 6: Pose Refinement – Foot & Hand Orientation
Scripts for foot and hand direction calculation. | Team A (2D focus): | Team B (3D focus):
Test visualizations (Blender or 3D JSON viewer). | Investigate ankle joint movement → deduce foot direction (forward vector). | Analyze wrist and elbow orientation for estimating palm/finger direction.
| Use keypoint trajectories + relative joint angles. | Optional: Add vector estimation from mid-wrist to index/thumb proxy point (if present).
Week 7: Confidence-Aware Triangulation
Confidence-weighted triangulation module. | Team A (2D focus): | Team B (3D focus):
Accuracy/reprojection error report comparing strategies. | Develop scoring function to weigh triangulated joints by 2D confidence. | Integrate probabilistic triangulation (early version).
| Try geometric median vs. simple average. | Compare with baseline triangulation pipeline.
Week 8: Final Integration & Documentation
All Members:
Finalize modules (confidence filtering, occlusion, smoothing, foot/hand estimation).
Package the entire workflow into callable scripts/functions for Unreal pipeline.
Write documentation & present findings internally.
Deliverables:
Stable integrated pose estimation & reconstruction module.
Usage + contribution doc.
GDrive folder with test outputs & code.
Optional Stretch Tasks (if any week ends early)
Try one deep-learning-based temporal smoothing approach (GRU/LSTM-based).
Implement real-time frame-by-frame logging or heatmaps of confidence anomalies.

## Pose Pipeline
Pose pipeline | Current status | Problem statements | Approaches/Options | Who's involved | Current timeline
Calibration | Uses triangulation code from Ball Tracking | Combine the current pipeline as a whole. Improve for better operator exp |  | Vedanshu / Akash
Providing live image for processing | Currently Not in Dev | Live ingest pipeline with Emergent cams or Z cams |  | Kanishka / Shivam | Z/PT cams cam ingest pipeline by end of July
Tracking (crop) and ReID | Dummy data (from StiQY) annotated and ready, training setup and algo training remaining | Tracking and classifying players across cameras and assigning a single ID as a part of 3D data | Data from player tracking | Shivam
2D pose detection
- Skeleton | RTMpose - 17 points | Currently doesn't include joints past wrist or ankle. | Review of other models [https://docs.google.com/document/d/1eCzltdDoa6EtZgXU_DgJuMFqg5GtYNv2_Be9_EVepyU/edit?tab=t.0] | Soumyadeep / interns | 2025-06-13
- Bat | Object included in optitrack data as a part of ground truth data collection | How to track and obtain position and rotation | Extension of skeleton, or separate prop | Soumyadeep
Training Data Generation | Data Collection Done, processing to be started | Reproject ground truth data from optitrack system on to 2D images collected from the cameras | Pipeline: Optitrack Data FBX --> Blender --> BVH --> 3D triangulated data --> Back calculation into 2D data using inverse calibration --> Reprojection on images (achieve time sync using clap for each clip) | Soumyadeep | 2025-06-20
2D post processing | Initial work done on 2D occlusion using kalman filter | Generate insights on comparison of smoothening effects on a 2D and a 3D level | Compare accuracy between Smoothening on 2D data during occlusions and jitter using kalman filer, swapped arms/legs etc. vs smoothening in 3D using 3D filters | Interns
3D triangulation | Uses triangulation code from Ball Tracking | Combine the current pipeline as a whole. Improve for better operator exp |  | Akash / Soumyadeep / Shivam
3D post processing | To be started | Understand and implement algorithms that can handle occlusion and smoothen jitters in 3D. Understand and implement IK and human physics elements | Research to be done | Interns
3D tranlate to Unreal | 3D point translation to BVH and visualisation to blender is done. This pipeline is not live. Code and data formats for livelink json's defined. | Create a pipeline to create a live/ near live pipelie of 2D pose to Unreal. This also involves axis and orientation matching | BVH or Livelink | Soumyadeep / Unreal generalists or developers
Unreal retargeting and smoothing |  |  |  | Generalists led by Nathan
2D algoritm
2D occlusion
2D temporal / smoothing experiements
3D confidence bias
Ideally leave occlusion for week 5 and 6. Target for month 1 that the pose and the algorithm can be recreated into unreal as a part of a working pipeline.
Flip the plan - and give intervention and smoothing to the unreal end
Rahat objectives
Bat
Integration of optitrack - to help with bat annotation
Integration of Unreal

## Next Steps and approaches for O
Domain | Task | Sub-Task | Potential Approach | Future Scope
BVH & Animation | Finalize BVH and Retargeting for Unreal Engine | Transform custom BVH to match cc_skeleton standards | Implement a script to transform the skeleton by matching bone offsets, hierarchy, and rotation orders.[minute changes needed]
|  | Address bone length mismatches during animation | Use Inverse Kinematics (IK) as a post-processing step to clean up final animations and enforce correct bone lengths.
|  | Correct sudden direction changes | Analyze and correct the axis mapping for foot and toe joints during the BVH export process.
|  | Ensure BVH meets Motion Builder requirements | Modify the BVH export to include required root translations and specific hip offset values.
Motion Quality | Implement Ground-Level Correction ("Foot Lock") | Integrate the estimated 3D ground plane topology into the post-processing pipeline. | Use an Inverse Kinematics (IK) solver where the end-effectors (feet) are constrained to stay on or above the calculated 3D round plane. | Apply similar constraints to other player-environment interactions
|  | Eliminate the "skating" effect caused by root node drifting. | The IK-based plane constraint should solve this by locking the feet to the ground during contact.
3D Accuracy | Enhance Triangulation and 3D Accuracy | Experiment with and evaluate non-linear triangulation methods. | Explore libraries offering non-linear optimization like bundle adjustment to minimize reprojection errors more effectively. | Integrate the best-performing method as the new default for the 3D reconstruction module.
|  | Develop and test the "Reverse Triangulation" approach. | Use PyTorch to project a 3D point back into the 2D heatmaps from RTMPose and optimize for the position that maximizes combined confidence.
Motion Quality | Implement Advanced Motion Smoothing & Refinement | Define and implement anatomical constraints for joints. | Implement a biomechanical model with hard constraints on joint rotation angles (e.g., prevent knees/elbows from bending backward). | Create a library of motion priors for different actions (bowling, batting) for specialized correction.
|  | Filter out or correct physically implausible poses. | Use a corrective model, trained on high-quality MoCap data (e.g. from OptiTrack) to learn and fix common triangulation errors. | Leverage MocapNet for 3d pose/triangulation correction. Try out different 3d reconstruction models like Neuro Rendering as suggested by Anshuman
BAT Tracking | Develop and Integrate Full Bat Pose Estimation | Complete data annotation for 2D bat keypoints using CVAT | Use the annotated data to train a dedicated 2D pose model for the bat (e.g., a fine-tuned RTMPose).
|  | Triangulate 2D bat keypoints into a 3D pose. | Apply the existing (or enhanced) triangulation pipeline to the bat's 2D keypoints.
|  | Attach the 3D bat model to the player's hands. | Parent the bat's root bone to the player's hand/wrist bone within the BVH hierarchy during the export process.
Pipeline & Performance | Automate and Optimize the Full Pipeline | Combine individual scripts into a single automated workflow | Create a master script or workflow manager that sequentially runs detection, tracking, triangulation, and BVH generation.(player tracker needs to be added) | Establish a stable LiveLink pipeline for real-time motion preview directly in Unreal Engine.
|  | Further optimize performance to meet the 30-40s target | Develop custom CUDA kernels for remaining computational bottlenecks like multi-person pose matching or refinement algorithms.
|  | Accelerate data loading and preprocessing | Fully integrate the NVIDIA DALI pipeline originally for ball tracking/ the AQuracy frame ingest pipeline and marrying the player ReIDs to handle the pose estimation input frames.

## Progress and outputs
Task Category | Task Completed | Progress & Status | Output / Link
Core Pose Estimation | 2D Pose Model Selection | Evaluated Yolov7/v8-pose, OpenPose, and Mediapipe. Selected RTMPose2D for its superior speed and accuracy. | Proposal for Real-Time 3D Reconstruction
| 2D Multi-Person Detection | Implemented multi-person 2D detection and skeleton construction. | 3d pose estimation (WEEK 2 Summary)
| Player ID Tracking | Solved temporal re-identification using a mean-based matching algorithm with the Hungarian method. | 3d pose estimation (WEEK 2 Summary)
Jitter & Occlusion | Jitter Removal | Implemented Savitzky-Golay Filter on 2D points, which successfully reduced jitter in the final 3D output. | 3d pose estimation (WEEK 1 Summary)
| Occlusion Handling | Designed and implemented a pipeline using an Unscented Kalman Filter (UKF) to predict the position of occluded joints based on motion analysis. | 3d pose estimation (WEEK 3+4 Summary)
| Occlusion Detection | Implemented an IOU-based method to flag tracked persons during heavy overlap, preventing their data from being used in triangulation. | 3d pose estimation (WEEK 7+8 Summary)
3D Reconstruction | 3D Triangulation | Implemented and tested multiple methods: best camera pair, confidence-weighted average of all pairs, and median of all pairs. | 3d pose estimation (WEEK 3+4 Summary)
| 3D Reprojection Error | Achieved a reprojection error of ~0.5 using a four-camera setup with confidence-based weighted averaging. | Proposal for Real-Time 3D Reconstruction (3.4)
| Ground Plane Estimation | Successfully estimated the ground plane topology from on-field markers using a quadratic surface fit, which was more accurate than a linear plane. | 3d pose estimation (WEEK 5+6)
GPU & Performance | UKF GPU Acceleration | Migrated the UKF implementation to the GPU using the torchfilter library, reducing CPU load from ~85% to ~50% during multi-person tracking. | 3d pose estimation (WEEK 7+8)
BVH & Unreal | BVH Generation & Integration | Successfully created a pipeline to convert 3D pose data into a BVH file and import it for seamless playback in Unreal Engine. | Proposal for Real-Time 3D Reconstruction (3.4, What we have achieved so far)
Data & Experiments | Manual Annotation Tool | Created an interactive tool to manually assign persistent global IDs to players across multiple cameras for initializing and validating tracking. | 3d pose estimation (WEEK 7+8 Summary)
| OptiTrack Comparison | Initiated experiments to collect data with the OptiTrack system to use as ground truth for comparison with the vision-based system. | Proposal for Real-Time 3D Reconstruction (8.3)
| Goa Runout Data | Processed videos from Goa (16th March) for stabilization and 2D/3D pose extraction. | 3D Pose in Blender Link: Google Drive
| Code & Outputs | All outputs from the "3d pose estimation" document are available on the specified machine. | Path: /home/kartavya/output/ on fatboy03
Interns developments and outputs | https://drive.google.com/drive/folders/1j33Uh7YIt1cjJKCQydra_Hnum8g0G2F0?usp=sharing
Github | https://github.com/Quidich-Innovation-Labs-Private-Limited/MoQap.git